## Master Dashboard
TRU CONNECT: ENGINEERING ROADMAP
Source of truth: Documents 00–09. See 'Notes & Assumptions' sheet for scope decisions.
Sheet | Total Tasks | ⬜ Not Started | 🟦 In Progress | 🟨 Testing | 🟪 Review | 🟩 Complete | 🔴 Blocked | % Complete
Backend | 155 | 129 | 26 | 0 | 0 | 0 | 0 | 0%
Frontend | 87 | 72 | 8 | 0 | 0 | 7 | 0 | 8.046%
Database | 58 | 50 | 8 | 0 | 0 | 0 | 0 | 0%
API | 99 | 90 | 9 | 0 | 0 | 0 | 0 | 0%
Trust Engine | 34 | 34 | 0 | 0 | 0 | 0 | 0 | 0%
Testing | 35 | 33 | 0 | 2 | 0 | 0 | 0 | 0%
DevOps | 15 | 15 | 0 | 0 | 0 | 0 | 0 | 0%
Future Phases | 24 | 24 | 0 | 0 | 0 | 0 | 0 | 0%
GRAND TOTAL | 507 | 447 | 51 | 2 | 0 | 7 | 0 | 1.381%
Priority Legend |  | Status Legend
🟥 Critical |  | ⬜ Not Started
🟧 High |  | 🟦 In Progress
🟨 Medium |  | 🟨 Testing
🟩 Low |  | 🟪 Review
🟩 Complete
🔴 Blocked

## Backend
ID | Module | Feature | Task | Priority | Dependencies | Assigned To | Status
BE-001 | Authentication Domain | users | Create `users` Model (SQLAlchemy ORM) | 🟥 Critical | DB-001 |  | 🟦 In Progress
BE-002 | Authentication Domain | users | Create `users` Repository (data access layer) | 🟥 Critical | BE-001 |  | 🟦 In Progress
BE-003 | Authentication Domain | roles | Create `roles` Model (SQLAlchemy ORM) | 🟧 High | DB-002 |  | 🟦 In Progress
BE-004 | Authentication Domain | roles | Create `roles` Repository (data access layer) | 🟧 High | BE-003 |  | 🟦 In Progress
BE-005 | Authentication Domain | permissions | Create `permissions` Model (SQLAlchemy ORM) | 🟧 High | DB-003 |  | 🟦 In Progress
BE-006 | Authentication Domain | permissions | Create `permissions` Repository (data access layer) | 🟧 High | BE-005 |  | 🟦 In Progress
BE-007 | Authentication Domain | role_permissions | Create `role_permissions` Model (SQLAlchemy ORM) | 🟧 High | DB-004 |  | 🟦 In Progress
BE-008 | Authentication Domain | role_permissions | Create `role_permissions` Repository (data access layer) | 🟧 High | BE-007 |  | 🟦 In Progress
BE-009 | Authentication Domain | user_roles | Create `user_roles` Model (SQLAlchemy ORM) | 🟧 High | DB-005 |  | 🟦 In Progress
BE-010 | Authentication Domain | user_roles | Create `user_roles` Repository (data access layer) | 🟧 High | BE-009 |  | 🟦 In Progress
BE-011 | Authentication Domain | refresh_tokens | Create `refresh_tokens` Model (SQLAlchemy ORM) | 🟧 High | DB-006 |  | 🟦 In Progress
BE-012 | Authentication Domain | refresh_tokens | Create `refresh_tokens` Repository (data access layer) | 🟧 High | BE-011 |  | 🟦 In Progress
BE-013 | Authentication Domain | login_history | Create `login_history` Model (SQLAlchemy ORM) | 🟧 High | DB-007 |  | 🟦 In Progress
BE-014 | Authentication Domain | login_history | Create `login_history` Repository (data access layer) | 🟧 High | BE-013 |  | 🟦 In Progress
BE-015 | Authentication Domain | password_reset_tokens | Create `password_reset_tokens` Model (SQLAlchemy ORM) | 🟧 High | DB-008 |  | 🟦 In Progress
BE-016 | Authentication Domain | password_reset_tokens | Create `password_reset_tokens` Repository (data access layer) | 🟧 High | BE-015 |  | 🟦 In Progress
BE-017 | Business Domain | businesses | Create `businesses` Model (SQLAlchemy ORM) | 🟥 Critical | DB-009 |  | ⬜ Not Started
BE-018 | Business Domain | businesses | Create `businesses` Repository (data access layer) | 🟥 Critical | BE-017 |  | ⬜ Not Started
BE-019 | Business Domain | business_profiles | Create `business_profiles` Model (SQLAlchemy ORM) | 🟧 High | DB-010 |  | ⬜ Not Started
BE-020 | Business Domain | business_profiles | Create `business_profiles` Repository (data access layer) | 🟧 High | BE-019 |  | ⬜ Not Started
BE-021 | Business Domain | business_addresses | Create `business_addresses` Model (SQLAlchemy ORM) | 🟧 High | DB-011 |  | ⬜ Not Started
BE-022 | Business Domain | business_addresses | Create `business_addresses` Repository (data access layer) | 🟧 High | BE-021 |  | ⬜ Not Started
BE-023 | Business Domain | business_categories | Create `business_categories` Model (SQLAlchemy ORM) | 🟧 High | DB-012 |  | ⬜ Not Started
BE-024 | Business Domain | business_categories | Create `business_categories` Repository (data access layer) | 🟧 High | BE-023 |  | ⬜ Not Started
BE-025 | Business Domain | business_documents | Create `business_documents` Model (SQLAlchemy ORM) | 🟧 High | DB-013 |  | ⬜ Not Started
BE-026 | Business Domain | business_documents | Create `business_documents` Repository (data access layer) | 🟧 High | BE-025 |  | ⬜ Not Started
BE-027 | Business Domain | business_settings | Create `business_settings` Model (SQLAlchemy ORM) | 🟧 High | DB-014 |  | ⬜ Not Started
BE-028 | Business Domain | business_settings | Create `business_settings` Repository (data access layer) | 🟧 High | BE-027 |  | ⬜ Not Started
BE-029 | Business Domain | business_bookmarks | Create `business_bookmarks` Model (SQLAlchemy ORM) | 🟧 High | DB-015 |  | ⬜ Not Started
BE-030 | Business Domain | business_bookmarks | Create `business_bookmarks` Repository (data access layer) | 🟧 High | BE-029 |  | ⬜ Not Started
BE-031 | Supplier Domain | suppliers | Create `suppliers` Model (SQLAlchemy ORM) | 🟥 Critical | DB-016 |  | ⬜ Not Started
BE-032 | Supplier Domain | suppliers | Create `suppliers` Repository (data access layer) | 🟥 Critical | BE-031 |  | ⬜ Not Started
BE-033 | Supplier Domain | supplier_profiles | Create `supplier_profiles` Model (SQLAlchemy ORM) | 🟧 High | DB-017 |  | ⬜ Not Started
BE-034 | Supplier Domain | supplier_profiles | Create `supplier_profiles` Repository (data access layer) | 🟧 High | BE-033 |  | ⬜ Not Started
BE-035 | Supplier Domain | supplier_categories | Create `supplier_categories` Model (SQLAlchemy ORM) | 🟧 High | DB-018 |  | ⬜ Not Started
BE-036 | Supplier Domain | supplier_categories | Create `supplier_categories` Repository (data access layer) | 🟧 High | BE-035 |  | ⬜ Not Started
BE-037 | Supplier Domain | supplier_products | Create `supplier_products` Model (SQLAlchemy ORM) | 🟥 Critical | DB-019 |  | ⬜ Not Started
BE-038 | Supplier Domain | supplier_products | Create `supplier_products` Repository (data access layer) | 🟥 Critical | BE-037 |  | ⬜ Not Started
BE-039 | Supplier Domain | supplier_product_images | Create `supplier_product_images` Model (SQLAlchemy ORM) | 🟧 High | DB-020 |  | ⬜ Not Started
BE-040 | Supplier Domain | supplier_product_images | Create `supplier_product_images` Repository (data access layer) | 🟧 High | BE-039 |  | ⬜ Not Started
BE-041 | Supplier Domain | supplier_delivery_regions | Create `supplier_delivery_regions` Model (SQLAlchemy ORM) | 🟧 High | DB-021 |  | ⬜ Not Started
BE-042 | Supplier Domain | supplier_delivery_regions | Create `supplier_delivery_regions` Repository (data access layer) | 🟧 High | BE-041 |  | ⬜ Not Started
BE-043 | Supplier Domain | supplier_business_hours | Create `supplier_business_hours` Model (SQLAlchemy ORM) | 🟧 High | DB-022 |  | ⬜ Not Started
BE-044 | Supplier Domain | supplier_business_hours | Create `supplier_business_hours` Repository (data access layer) | 🟧 High | BE-043 |  | ⬜ Not Started
BE-045 | Supplier Domain | supplier_updates | Create `supplier_updates` Model (SQLAlchemy ORM) | 🟧 High | DB-023 |  | ⬜ Not Started
BE-046 | Supplier Domain | supplier_updates | Create `supplier_updates` Repository (data access layer) | 🟧 High | BE-045 |  | ⬜ Not Started
BE-047 | Marketplace Domain | orders | Create `orders` Model (SQLAlchemy ORM) | 🟥 Critical | DB-024 |  | ⬜ Not Started
BE-048 | Marketplace Domain | orders | Create `orders` Repository (data access layer) | 🟥 Critical | BE-047 |  | ⬜ Not Started
BE-049 | Marketplace Domain | order_items | Create `order_items` Model (SQLAlchemy ORM) | 🟥 Critical | DB-025 |  | ⬜ Not Started
BE-050 | Marketplace Domain | order_items | Create `order_items` Repository (data access layer) | 🟥 Critical | BE-049 |  | ⬜ Not Started
BE-051 | Marketplace Domain | business_questions | Create `business_questions` Model (SQLAlchemy ORM) | 🟧 High | DB-026 |  | ⬜ Not Started
BE-052 | Marketplace Domain | business_questions | Create `business_questions` Repository (data access layer) | 🟧 High | BE-051 |  | ⬜ Not Started
BE-053 | Marketplace Domain | supplier_responses | Create `supplier_responses` Model (SQLAlchemy ORM) | 🟧 High | DB-027 |  | ⬜ Not Started
BE-054 | Marketplace Domain | supplier_responses | Create `supplier_responses` Repository (data access layer) | 🟧 High | BE-053 |  | ⬜ Not Started
BE-055 | Marketplace Domain | product_views | Create `product_views` Model (SQLAlchemy ORM) | 🟧 High | DB-028 |  | ⬜ Not Started
BE-056 | Marketplace Domain | product_views | Create `product_views` Repository (data access layer) | 🟧 High | BE-055 |  | ⬜ Not Started
BE-057 | Marketplace Domain | saved_products | Create `saved_products` Model (SQLAlchemy ORM) | 🟧 High | DB-029 |  | ⬜ Not Started
BE-058 | Marketplace Domain | saved_products | Create `saved_products` Repository (data access layer) | 🟧 High | BE-057 |  | ⬜ Not Started
BE-059 | Marketplace Domain | saved_suppliers | Create `saved_suppliers` Model (SQLAlchemy ORM) | 🟧 High | DB-030 |  | ⬜ Not Started
BE-060 | Marketplace Domain | saved_suppliers | Create `saved_suppliers` Repository (data access layer) | 🟧 High | BE-059 |  | ⬜ Not Started
BE-061 | Trust Domain | business_supplier_relationships | Create `business_supplier_relationships` Model (SQLAlchemy ORM) | 🟥 Critical | DB-031 |  | ⬜ Not Started
BE-062 | Trust Domain | business_supplier_relationships | Create `business_supplier_relationships` Repository (data access layer) | 🟥 Critical | BE-061 |  | ⬜ Not Started
BE-063 | Trust Domain | relationship_events | Create `relationship_events` Model (SQLAlchemy ORM) | 🟧 High | DB-032 |  | ⬜ Not Started
BE-064 | Trust Domain | relationship_events | Create `relationship_events` Repository (data access layer) | 🟧 High | BE-063 |  | ⬜ Not Started
BE-065 | Trust Domain | trust_signals | Create `trust_signals` Model (SQLAlchemy ORM) | 🟧 High | DB-033 |  | ⬜ Not Started
BE-066 | Trust Domain | trust_signals | Create `trust_signals` Repository (data access layer) | 🟧 High | BE-065 |  | ⬜ Not Started
BE-067 | Trust Domain | business_health_scores | Create `business_health_scores` Model (SQLAlchemy ORM) | 🟧 High | DB-034 |  | ⬜ Not Started
BE-068 | Trust Domain | business_health_scores | Create `business_health_scores` Repository (data access layer) | 🟧 High | BE-067 |  | ⬜ Not Started
BE-069 | Trust Domain | supplier_reputation_scores | Create `supplier_reputation_scores` Model (SQLAlchemy ORM) | 🟧 High | DB-035 |  | ⬜ Not Started
BE-070 | Trust Domain | supplier_reputation_scores | Create `supplier_reputation_scores` Repository (data access layer) | 🟧 High | BE-069 |  | ⬜ Not Started
BE-071 | Trust Domain | trust_score_history | Create `trust_score_history` Model (SQLAlchemy ORM) | 🟧 High | DB-036 |  | ⬜ Not Started
BE-072 | Trust Domain | trust_score_history | Create `trust_score_history` Repository (data access layer) | 🟧 High | BE-071 |  | ⬜ Not Started
BE-073 | Verification Domain | verification_requests | Create `verification_requests` Model (SQLAlchemy ORM) | 🟧 High | DB-037 |  | ⬜ Not Started
BE-074 | Verification Domain | verification_requests | Create `verification_requests` Repository (data access layer) | 🟧 High | BE-073 |  | ⬜ Not Started
BE-075 | Verification Domain | verification_documents | Create `verification_documents` Model (SQLAlchemy ORM) | 🟧 High | DB-038 |  | ⬜ Not Started
BE-076 | Verification Domain | verification_documents | Create `verification_documents` Repository (data access layer) | 🟧 High | BE-075 |  | ⬜ Not Started
BE-077 | Verification Domain | verification_history | Create `verification_history` Model (SQLAlchemy ORM) | 🟧 High | DB-039 |  | ⬜ Not Started
BE-078 | Verification Domain | verification_history | Create `verification_history` Repository (data access layer) | 🟧 High | BE-077 |  | ⬜ Not Started
BE-079 | Platform Domain | notifications | Create `notifications` Model (SQLAlchemy ORM) | 🟧 High | DB-040 |  | ⬜ Not Started
BE-080 | Platform Domain | notifications | Create `notifications` Repository (data access layer) | 🟧 High | BE-079 |  | ⬜ Not Started
BE-081 | Platform Domain | notification_preferences | Create `notification_preferences` Model (SQLAlchemy ORM) | 🟨 Medium | DB-041 |  | ⬜ Not Started
BE-082 | Platform Domain | notification_preferences | Create `notification_preferences` Repository (data access layer) | 🟨 Medium | BE-081 |  | ⬜ Not Started
BE-083 | Platform Domain | audit_logs | Create `audit_logs` Model (SQLAlchemy ORM) | 🟨 Medium | DB-042 |  | ⬜ Not Started
BE-084 | Platform Domain | audit_logs | Create `audit_logs` Repository (data access layer) | 🟨 Medium | BE-083 |  | ⬜ Not Started
BE-085 | Platform Domain | system_settings | Create `system_settings` Model (SQLAlchemy ORM) | 🟨 Medium | DB-043 |  | ⬜ Not Started
BE-086 | Platform Domain | system_settings | Create `system_settings` Repository (data access layer) | 🟨 Medium | BE-085 |  | ⬜ Not Started
BE-087 | Platform Domain | lookup_categories | Create `lookup_categories` Model (SQLAlchemy ORM) | 🟨 Medium | DB-044 |  | ⬜ Not Started
BE-088 | Platform Domain | lookup_categories | Create `lookup_categories` Repository (data access layer) | 🟨 Medium | BE-087 |  | ⬜ Not Started
BE-089 | Platform Domain | provinces | Create `provinces` Model (SQLAlchemy ORM) | 🟨 Medium | DB-045 |  | ⬜ Not Started
BE-090 | Platform Domain | provinces | Create `provinces` Repository (data access layer) | 🟨 Medium | BE-089 |  | ⬜ Not Started
BE-091 | Platform Domain | cities | Create `cities` Model (SQLAlchemy ORM) | 🟨 Medium | DB-046 |  | ⬜ Not Started
BE-092 | Platform Domain | cities | Create `cities` Repository (data access layer) | 🟨 Medium | BE-091 |  | ⬜ Not Started
BE-093 | Authentication Domain | Registration (Business) | Registration Service — Business: create business + zero-state Digital Business Profile (Document 06 §1) | 🟥 Critical | See linked domain models |  | 🟦 In Progress
BE-094 | Authentication Domain | Registration (Business) | Business Registration request Schema (name, category, location, contact number) | 🟥 Critical | See linked domain models |  | ⬜ Not Started
BE-095 | Authentication Domain | Registration (Business) | Enforce one-role-per-account constraint at registration (Document 06 §1) | 🟧 High | See linked domain models |  | ⬜ Not Started
BE-096 | Authentication Domain | Registration (Supplier) | Registration Service — Supplier: create supplier + zero-state Supplier Profile (Document 06 §2) | 🟥 Critical | See linked domain models |  | ⬜ Not Started
BE-097 | Authentication Domain | Registration (Supplier) | Supplier Registration request Schema (name, category, regions served, contact number) | 🟥 Critical | See linked domain models |  | ⬜ Not Started
BE-098 | Authentication Domain | Registration (Supplier) | Enforce supplier cannot publish products until profile is complete (Document 06 §2) | 🟧 High | See linked domain models |  | ⬜ Not Started
BE-099 | Authentication Domain | Login | Login Service — email/password credential verification + login_history entry | 🟥 Critical | See linked domain models |  | 🟦 In Progress
BE-100 | Authentication Domain | Login | Google OAuth Service — verify Google token, create or match account | 🟥 Critical | See linked domain models |  | ⬜ Not Started
BE-101 | Authentication Domain | Token Management | Refresh Token Service — issue, validate, rotate refresh tokens | 🟥 Critical | See linked domain models |  | ⬜ Not Started
BE-102 | Authentication Domain | Token Management | Logout Service — revoke current refresh_token | 🟧 High | See linked domain models |  | ⬜ Not Started
BE-103 | Authentication Domain | Password Reset | Forgot Password Service — create password_reset_tokens entry, send email | 🟧 High | See linked domain models |  | ⬜ Not Started
BE-104 | Authentication Domain | Password Reset | Reset Password Service — validate reset token, update password_hash | 🟧 High | See linked domain models |  | ⬜ Not Started
BE-105 | Authentication Domain | Authorization | Role Authorization Decorator — enforce roles/permissions/role_permissions/user_roles (Document 04 §7 note 5) | 🟥 Critical | See linked domain models |  | ⬜ Not Started
BE-106 | Verification Domain | Verification | Verification Service — submit request (business or supplier) with documents (Document 06 §3) | 🟧 High | See linked domain models |  | ⬜ Not Started
BE-107 | Verification Domain | Verification | Verification Service — approve request: set is_verified flag + verification badge (Document 06 §3) | 🟧 High | See linked domain models |  | ⬜ Not Started
BE-108 | Verification Domain | Verification | Verification Service — reject request: internal reviewer_notes only, generic message to user (Document 06 §3) | 🟧 High | See linked domain models |  | ⬜ Not Started
BE-109 | Verification Domain | Verification | Enforce Featured Suppliers listing requires approved verification (Document 06 §3) | 🟨 Medium | See linked domain models |  | ⬜ Not Started
BE-110 | Supplier Domain | Product Listing | Product Service — create product, enforce exactly one category (Document 06 §4) | 🟥 Critical | See linked domain models |  | ⬜ Not Started
BE-111 | Supplier Domain | Product Listing | Product Service — draft vs published (is_published flag) on create (Document 06 §4) | 🟧 High | See linked domain models |  | ⬜ Not Started
BE-112 | Supplier Domain | Product Listing | Product Service — update stock_status (in_stock/low_stock/out_of_stock) | 🟧 High | See linked domain models |  | ⬜ Not Started
BE-113 | Supplier Domain | Product Listing | Exclude out_of_stock products from Popular Products ranking (Document 06 §4) | 🟨 Medium | See linked domain models |  | ⬜ Not Started
BE-114 | Supplier Domain | Product Listing | Product Service — soft-delete/unpublish on delete, preserve Order Item history (Document 06 §4) | 🟥 Critical | See linked domain models |  | ⬜ Not Started
BE-115 | Supplier Domain | Supplier Discovery | Supplier Search Service — ranking by relevance, verification status, distance, relationship signal (Document 06 §5) | 🟧 High | See linked domain models |  | ⬜ Not Started
BE-116 | Supplier Domain | Supplier Discovery | Supplier Search Service — "Verified only" filter (Document 06 §5) | 🟨 Medium | See linked domain models |  | ⬜ Not Started
BE-117 | Marketplace Domain | Viewing Products | Product View Service — log product_views event on Product Detail open (Document 06 §6) | 🟨 Medium | See linked domain models |  | ⬜ Not Started
BE-118 | Marketplace Domain | Business Questions | Business Question Service — create question with category enum (Document 06 §7) | 🟧 High | See linked domain models |  | ⬜ Not Started
BE-119 | Marketplace Domain | Business Questions | Business Question Service — notify supplier of new unanswered question (Document 06 §7) | 🟧 High | See linked domain models |  | ⬜ Not Started
BE-120 | Marketplace Domain | Supplier Responses | Supplier Response Service — create response, enforce one official response per question (Document 06 §8) | 🟧 High | See linked domain models |  | ⬜ Not Started
BE-121 | Marketplace Domain | Supplier Responses | Supplier Response Service — update average_response_time_minutes and response_rate_percentage (Document 06 §8) | 🟧 High | See linked domain models |  | ⬜ Not Started
BE-122 | Marketplace Domain | Bookmark Supplier | Bookmark Service — create saved_suppliers entry, one-directional, no supplier notification (Document 06 §9) | 🟨 Medium | See linked domain models |  | ⬜ Not Started
BE-123 | Marketplace Domain | Place Order | Order Service — enforce single-supplier-only cart (Document 06 §10) | 🟥 Critical | See linked domain models |  | ⬜ Not Started
BE-124 | Marketplace Domain | Place Order | Order Service — enforce minimum order quantity per product line (Document 06 §10) | 🟥 Critical | See linked domain models |  | ⬜ Not Started
BE-125 | Marketplace Domain | Place Order | Order Service — lock unit_price_at_order_time using current price + bulk pricing rules (Document 06 §10) | 🟥 Critical | See linked domain models |  | ⬜ Not Started
BE-126 | Marketplace Domain | Accept Order | Order Service — accept: transition status, set accepted_at, notify business (Document 06 §11) | 🟥 Critical | See linked domain models |  | ⬜ Not Started
BE-127 | Marketplace Domain | Reject Order | Order Service — reject: require reason, transition status, notify business (Document 06 §12) | 🟥 Critical | See linked domain models |  | ⬜ Not Started
BE-128 | Marketplace Domain | Reject Order | Exclude rejected orders from repeat-order/trust calculations (Document 06 §12) | 🟨 Medium | See linked domain models |  | ⬜ Not Started
BE-129 | Marketplace Domain | Complete Order | Order Service — complete: transition status, set completed_at, generate invoice (Document 06 §13) | 🟥 Critical | See linked domain models |  | ⬜ Not Started
BE-130 | Marketplace Domain | Complete Order | Order Service — trigger Business Profile + Supplier Profile recalculation on completion (Document 06 §13) | 🟥 Critical | See linked domain models |  | ⬜ Not Started
BE-131 | Marketplace Domain | Order History | Enforce order history immutability once a terminal status is reached (Document 06 §14) | 🟨 Medium | See linked domain models |  | ⬜ Not Started
BE-132 | Trust Domain | Profile Recalculation | Async Job — recalculate Business Profile on order placed (Document 06 §15) | 🟧 High | See linked domain models |  | ⬜ Not Started
BE-133 | Trust Domain | Profile Recalculation | Async Job — recalculate Business Profile on order completed (Document 06 §15) | 🟧 High | See linked domain models |  | ⬜ Not Started
BE-134 | Trust Domain | Profile Recalculation | Async Job — recalculate Business Profile on order cancelled/rejected (Document 06 §15) | 🟧 High | See linked domain models |  | ⬜ Not Started
BE-135 | Trust Domain | Profile Recalculation | Async Job — recalculate Business Profile on new supplier relationship established (Document 06 §15) | 🟧 High | See linked domain models |  | ⬜ Not Started
BE-136 | Trust Domain | Profile Recalculation | Async Job — recalculate Business Profile on verification status change (Document 06 §15) | 🟧 High | See linked domain models |  | ⬜ Not Started
BE-137 | Trust Domain | Profile Recalculation | Async Job — recalculate Supplier Profile on order received/accepted/rejected/completed (Document 06 §16) | 🟧 High | See linked domain models |  | ⬜ Not Started
BE-138 | Trust Domain | Profile Recalculation | Async Job — recalculate Supplier Profile on Business Question response submitted (Document 06 §16) | 🟧 High | See linked domain models |  | ⬜ Not Started
BE-139 | Trust Domain | Trust Updates | Async job runner — non-blocking recalculation queue (Document 06 §17) | 🟥 Critical | See linked domain models |  | ⬜ Not Started
BE-140 | Trust Domain | Trust Updates | Relationship-level statistics update per business-supplier pair (Document 06 §17) | 🟧 High | See linked domain models |  | ⬜ Not Started
BE-141 | Platform Domain | Notifications | Notification Service — order status change (sync delivery, Document 06 §18) | 🟥 Critical | See linked domain models |  | ⬜ Not Started
BE-142 | Platform Domain | Notifications | Notification Service — Business Question response (sync delivery, Document 06 §18) | 🟧 High | See linked domain models |  | ⬜ Not Started
BE-143 | Platform Domain | Notifications | Notification Service — Business Update fan-out to followers (Document 06 §18) | 🟧 High | See linked domain models |  | ⬜ Not Started
BE-144 | Platform Domain | Notifications | Notification Service — verification status change (sync delivery, Document 06 §18) | 🟧 High | See linked domain models |  | ⬜ Not Started
BE-145 | Business Domain | Account Integrity | Account Service — deactivation: hide from discovery, preserve history (Document 06 §19) | 🟨 Medium | See linked domain models |  | ⬜ Not Started
BE-146 | Cross-Domain | Core Infrastructure | config.py — environment-based configuration (dev/staging/prod) | 🟥 Critical | None |  | 🟦 In Progress
BE-147 | Cross-Domain | Core Infrastructure | extensions.py — initialise Flask extensions (SQLAlchemy, JWT, CORS) | 🟥 Critical | None |  | 🟦 In Progress
BE-148 | Cross-Domain | Core Infrastructure | base_model.py — shared model base class (UUID PK, created_at/updated_at) | 🟥 Critical | None |  | 🟦 In Progress
BE-149 | Cross-Domain | Core Infrastructure | decorators.py — role/permission enforcement decorators | 🟥 Critical | None |  | 🟦 In Progress
BE-150 | Cross-Domain | Core Infrastructure | exceptions.py — custom exception classes | 🟧 High | None |  | 🟦 In Progress
BE-151 | Cross-Domain | Core Infrastructure | responses.py — standard API response envelope (Document 05 §1 error structure) | 🟧 High | None |  | 🟦 In Progress
BE-152 | Cross-Domain | Core Infrastructure | logger.py — structured logging utility | 🟨 Medium | None |  | 🟦 In Progress
BE-153 | Cross-Domain | Core Infrastructure | security.py — password hashing + JWT token utilities | 🟥 Critical | None |  | 🟦 In Progress
BE-154 | Cross-Domain | Core Infrastructure | Pagination utility — shared page/page_size helper (Document 05 §1) | 🟧 High | None |  | ⬜ Not Started
BE-155 | Cross-Domain | Core Infrastructure | JWT Service — issue, verify, refresh tokens (Document 05 §5.1) | 🟥 Critical | None |  | ⬜ Not Started

## Frontend
ID | Module | Feature | Task | Priority | Dependencies | Assigned To | Status
FE-001 | Shared / Pre-Auth | Screens | Build Landing Screen (two-slide role introduction) Screen | 🟧 High | Corresponding API endpoint(s) |  | 🟩 Complete
FE-002 | Shared / Pre-Auth | Screens | Build Login Screen Screen | 🟧 High | Corresponding API endpoint(s) |  | 🟩 Complete
FE-003 | Shared / Pre-Auth | Screens | Build Register Screen Screen | 🟧 High | Corresponding API endpoint(s) |  | 🟩 Complete
FE-004 | Shared / Pre-Auth | Screens | Build Google Authentication flow screen Screen | 🟧 High | Corresponding API endpoint(s) |  | ⬜ Not Started
FE-005 | Business (Doc01 §8.2) | Screens | Build Business Home Dashboard Screen | 🟧 High | Corresponding API endpoint(s) |  | 🟦 In Progress
FE-006 | Business (Doc01 §8.2) | Screens | Build Business Profile Screen | 🟧 High | Corresponding API endpoint(s) |  | ⬜ Not Started
FE-007 | Business (Doc01 §8.2) | Screens | Build Verification Screen | 🟧 High | Corresponding API endpoint(s) |  | ⬜ Not Started
FE-008 | Business (Doc01 §8.2) | Screens | Build Wallet (Phase 1 placeholder — Document 01 §8.2) Screen | 🟩 Low | Corresponding API endpoint(s) |  | ⬜ Not Started
FE-009 | Business (Doc01 §8.2) | Screens | Build Saved Suppliers Screen | 🟧 High | Corresponding API endpoint(s) |  | ⬜ Not Started
FE-010 | Business (Doc01 §8.2) | Screens | Add Loading State (skeleton) to Saved Suppliers — Document 02 §2.3 | 🟨 Medium | FE-009 |  | ⬜ Not Started
FE-011 | Business (Doc01 §8.2) | Screens | Add Empty State to Saved Suppliers — Document 02 §2.3 / Document 03 §5.9 | 🟨 Medium | FE-009 |  | ⬜ Not Started
FE-012 | Business (Doc01 §8.2) | Screens | Build Business Documents Screen | 🟧 High | Corresponding API endpoint(s) |  | ⬜ Not Started
FE-013 | Business (Doc01 §8.2) | Screens | Build Business Insights (Phase 1 placeholder — Document 01 §8.2) Screen | 🟩 Low | Corresponding API endpoint(s) |  | ⬜ Not Started
FE-014 | Business (Doc01 §8.2) | Screens | Build Supplier Search / Discovery Screen | 🟧 High | Corresponding API endpoint(s) |  | ⬜ Not Started
FE-015 | Business (Doc01 §8.2) | Screens | Add Loading State (skeleton) to Supplier Search / Discovery — Document 02 §2.3 | 🟨 Medium | FE-014 |  | ⬜ Not Started
FE-016 | Business (Doc01 §8.2) | Screens | Add Empty State to Supplier Search / Discovery — Document 02 §2.3 / Document 03 §5.9 | 🟨 Medium | FE-014 |  | ⬜ Not Started
FE-017 | Business (Doc01 §8.2) | Screens | Build Supplier Profile (public view) Screen | 🟧 High | Corresponding API endpoint(s) |  | ⬜ Not Started
FE-018 | Business (Doc01 §8.2) | Screens | Build Product Detail (with Business Questions thread) Screen | 🟧 High | Corresponding API endpoint(s) |  | ⬜ Not Started
FE-019 | Business (Doc01 §8.2) | Screens | Build Cart / Order Placement Screen | 🟧 High | Corresponding API endpoint(s) |  | ⬜ Not Started
FE-020 | Business (Doc01 §8.2) | Screens | Build Order List (current, pending, completed, cancelled) Screen | 🟧 High | Corresponding API endpoint(s) |  | ⬜ Not Started
FE-021 | Business (Doc01 §8.2) | Screens | Add Loading State (skeleton) to Order List (current, pending, completed, cancelled) — Document 02 §2.3 | 🟨 Medium | FE-020 |  | ⬜ Not Started
FE-022 | Business (Doc01 §8.2) | Screens | Add Empty State to Order List (current, pending, completed, cancelled) — Document 02 §2.3 / Document 03 §5.9 | 🟨 Medium | FE-020 |  | ⬜ Not Started
FE-023 | Business (Doc01 §8.2) | Screens | Build Order Detail / Delivery Tracking Screen | 🟧 High | Corresponding API endpoint(s) |  | ⬜ Not Started
FE-024 | Business (Doc01 §8.2) | Screens | Build Notifications Screen | 🟧 High | Corresponding API endpoint(s) |  | ⬜ Not Started
FE-025 | Business (Doc01 §8.2) | Screens | Add Loading State (skeleton) to Notifications — Document 02 §2.3 | 🟨 Medium | FE-024 |  | ⬜ Not Started
FE-026 | Business (Doc01 §8.2) | Screens | Add Empty State to Notifications — Document 02 §2.3 / Document 03 §5.9 | 🟨 Medium | FE-024 |  | ⬜ Not Started
FE-027 | Business (Doc01 §8.2) | Screens | Build Settings / More Screen | 🟧 High | Corresponding API endpoint(s) |  | ⬜ Not Started
FE-028 | Supplier (Doc01 §8.3) | Screens | Build Supplier Home Dashboard Screen | 🟧 High | Corresponding API endpoint(s) |  | 🟦 In Progress
FE-029 | Supplier (Doc01 §8.3) | Screens | Build Product Catalogue Management Screen | 🟧 High | Corresponding API endpoint(s) |  | 🟦 In Progress
FE-030 | Supplier (Doc01 §8.3) | Screens | Add Loading State (skeleton) to Product Catalogue Management — Document 02 §2.3 | 🟨 Medium | FE-029 |  | ⬜ Not Started
FE-031 | Supplier (Doc01 §8.3) | Screens | Add Empty State to Product Catalogue Management — Document 02 §2.3 / Document 03 §5.9 | 🟨 Medium | FE-029 |  | ⬜ Not Started
FE-032 | Supplier (Doc01 §8.3) | Screens | Build Product Create / Edit Screen | 🟧 High | Corresponding API endpoint(s) |  | 🟦 In Progress
FE-033 | Supplier (Doc01 §8.3) | Screens | Build Order List (incoming, accepted, completed, cancelled) Screen | 🟧 High | Corresponding API endpoint(s) |  | ⬜ Not Started
FE-034 | Supplier (Doc01 §8.3) | Screens | Add Loading State (skeleton) to Order List (incoming, accepted, completed, cancelled) — Document 02 §2.3 | 🟨 Medium | FE-033 |  | ⬜ Not Started
FE-035 | Supplier (Doc01 §8.3) | Screens | Add Empty State to Order List (incoming, accepted, completed, cancelled) — Document 02 §2.3 / Document 03 §5.9 | 🟨 Medium | FE-033 |  | ⬜ Not Started
FE-036 | Supplier (Doc01 §8.3) | Screens | Build Order Detail / Fulfilment Screen | 🟧 High | Corresponding API endpoint(s) |  | ⬜ Not Started
FE-037 | Supplier (Doc01 §8.3) | Screens | Build Customer Enquiries List Screen | 🟧 High | Corresponding API endpoint(s) |  | ⬜ Not Started
FE-038 | Supplier (Doc01 §8.3) | Screens | Add Loading State (skeleton) to Customer Enquiries List — Document 02 §2.3 | 🟨 Medium | FE-037 |  | ⬜ Not Started
FE-039 | Supplier (Doc01 §8.3) | Screens | Add Empty State to Customer Enquiries List — Document 02 §2.3 / Document 03 §5.9 | 🟨 Medium | FE-037 |  | ⬜ Not Started
FE-040 | Supplier (Doc01 §8.3) | Screens | Build Business Performance / Statistics Screen | 🟧 High | Corresponding API endpoint(s) |  | ⬜ Not Started
FE-041 | Supplier (Doc01 §8.3) | Screens | Build Business Updates Composer Screen | 🟧 High | Corresponding API endpoint(s) |  | ⬜ Not Started
FE-042 | Supplier (Doc01 §8.3) | Screens | Build Notifications Screen | 🟧 High | Corresponding API endpoint(s) |  | ⬜ Not Started
FE-043 | Supplier (Doc01 §8.3) | Screens | Add Loading State (skeleton) to Notifications — Document 02 §2.3 | 🟨 Medium | FE-042 |  | ⬜ Not Started
FE-044 | Supplier (Doc01 §8.3) | Screens | Add Empty State to Notifications — Document 02 §2.3 / Document 03 §5.9 | 🟨 Medium | FE-042 |  | ⬜ Not Started
FE-045 | Supplier (Doc01 §8.3) | Screens | Build Settings / More Screen | 🟧 High | Corresponding API endpoint(s) |  | ⬜ Not Started
FE-046 | Auth Components | Component Library (Document 03) | Build GoogleAuthButton Component | 🟧 High | Theme tokens |  | ⬜ Not Started
FE-047 | Auth Components | Component Library (Document 03) | Build RoleSelector Component | 🟧 High | Theme tokens |  | 🟩 Complete
FE-048 | Business Components | Component Library (Document 03) | Build BusinessSummaryCard Component | 🟧 High | Theme tokens |  | ⬜ Not Started
FE-049 | Business Components | Component Library (Document 03) | Build SupplierCard Component | 🟧 High | Theme tokens |  | ⬜ Not Started
FE-050 | Business Components | Component Library (Document 03) | Build ProductCard Component | 🟧 High | Theme tokens |  | ⬜ Not Started
FE-051 | Business Components | Component Library (Document 03) | Build OrderCard (Business view) Component | 🟧 High | Theme tokens |  | ⬜ Not Started
FE-052 | Business Components | Component Library (Document 03) | Build CategoryCard / Category Chips Component | 🟧 High | Theme tokens |  | ⬜ Not Started
FE-053 | Business Components | Component Library (Document 03) | Build BusinessQuestionThread Component | 🟧 High | Theme tokens |  | ⬜ Not Started
FE-054 | Business Components | Component Library (Document 03) | Build DigitalBusinessProfileCard Component | 🟧 High | Theme tokens |  | 🟦 In Progress
FE-055 | Supplier Components | Component Library (Document 03) | Build SupplierSummaryCard Component | 🟧 High | Theme tokens |  | ⬜ Not Started
FE-056 | Supplier Components | Component Library (Document 03) | Build CustomerCard Component | 🟧 High | Theme tokens |  | ⬜ Not Started
FE-057 | Supplier Components | Component Library (Document 03) | Build ProductManagementCard Component | 🟧 High | Theme tokens |  | 🟩 Complete
FE-058 | Supplier Components | Component Library (Document 03) | Build OrderCard (Supplier view) Component | 🟧 High | Theme tokens |  | ⬜ Not Started
FE-059 | Supplier Components | Component Library (Document 03) | Build BusinessPerformanceCard Component | 🟧 High | Theme tokens |  | ⬜ Not Started
FE-060 | Supplier Components | Component Library (Document 03) | Build BusinessUpdateComposer Component | 🟧 High | Theme tokens |  | ⬜ Not Started
FE-061 | Shared Components | Component Library (Document 03) | Build AppHeader Component | 🟧 High | Theme tokens |  | 🟦 In Progress
FE-062 | Shared Components | Component Library (Document 03) | Build SearchBar Component | 🟧 High | Theme tokens |  | ⬜ Not Started
FE-063 | Shared Components | Component Library (Document 03) | Build BottomNavigation Component | 🟧 High | Theme tokens |  | 🟦 In Progress
FE-064 | Shared Components | Component Library (Document 03) | Build StatisticsCard Component | 🟧 High | Theme tokens |  | ⬜ Not Started
FE-065 | Shared Components | Component Library (Document 03) | Build NotificationCard Component | 🟧 High | Theme tokens |  | ⬜ Not Started
FE-066 | Shared Components | Component Library (Document 03) | Build VerificationBadge Component | 🟧 High | Theme tokens |  | ⬜ Not Started
FE-067 | Shared Components | Component Library (Document 03) | Build CategoryChips Component | 🟧 High | Theme tokens |  | ⬜ Not Started
FE-068 | Shared Components | Component Library (Document 03) | Build ActionButton Component | 🟧 High | Theme tokens |  | 🟩 Complete
FE-069 | Shared Components | Component Library (Document 03) | Build EmptyState Component | 🟧 High | Theme tokens |  | 🟩 Complete
FE-070 | Shared Components | Component Library (Document 03) | Build LoadingState Component | 🟧 High | Theme tokens |  | ⬜ Not Started
FE-071 | Shared Components | Component Library (Document 03) | Build Modal Component | 🟧 High | Theme tokens |  | ⬜ Not Started
FE-072 | Shared Components | Component Library (Document 03) | Build Dialog Component | 🟧 High | Theme tokens |  | ⬜ Not Started
FE-073 | Cross-Cutting | Navigation | Configure Business Bottom Navigation (Home ¦ Business ¦ Suppliers ¦ Orders ¦ More) | 🟧 High | None |  | ⬜ Not Started
FE-074 | Cross-Cutting | Navigation | Configure Supplier Bottom Navigation (Home ¦ Products ¦ Orders ¦ Customers ¦ More) | 🟧 High | None |  | ⬜ Not Started
FE-075 | Cross-Cutting | Navigation | Implement role-based route guard/redirect after authentication | 🟥 Critical | None |  | 🟦 In Progress
FE-076 | Cross-Cutting | Navigation | Configure stack navigation drill-down within each tab (Document 02 §2.1) | 🟧 High | None |  | ⬜ Not Started
FE-077 | Cross-Cutting | Theme | Define type scale (Display/H1/H2/Body/Body Small/Caption — Document 02 §4) | 🟧 High | None |  | ⬜ Not Started
FE-078 | Cross-Cutting | Theme | Define light color palette by functional role (Document 02 §5) | 🟧 High | None |  | ⬜ Not Started
FE-079 | Cross-Cutting | Theme | Define dark mode palette (Document 02 §1.3 — future-ready, not required Phase 1) | 🟩 Low | None |  | ⬜ Not Started
FE-080 | Cross-Cutting | Theme | Define 4dp-based spacing scale (xs/sm/md/lg/xl — Document 02 §11) | 🟨 Medium | None |  | ⬜ Not Started
FE-081 | Cross-Cutting | Theme | Integrate single line-style icon set app-wide (Document 02 §10) | 🟨 Medium | None |  | ⬜ Not Started
FE-082 | Cross-Cutting | Accessibility | Verify 4.5:1 minimum contrast ratio for body text (Document 02 §13) | 🟨 Medium | None |  | ⬜ Not Started
FE-083 | Cross-Cutting | Accessibility | Add accessibilityLabel to every interactive element (Document 02 §13) | 🟨 Medium | None |  | ⬜ Not Started
FE-084 | Cross-Cutting | Accessibility | Support OS-level dynamic font scaling without breaking layout (Document 02 §13) | 🟨 Medium | None |  | ⬜ Not Started
FE-085 | Cross-Cutting | Animations | Implement standard screen transition + tab-switch animations (Document 02 §12) | 🟩 Low | None |  | ⬜ Not Started
FE-086 | Cross-Cutting | Animations | Implement shimmer loading skeleton for card-shaped content (Document 02 §12) | 🟩 Low | None |  | ⬜ Not Started
FE-087 | Cross-Cutting | Animations | Implement brief status-change confirmation animation (e.g. order accepted — Document 02 §12) | 🟩 Low | None |  | ⬜ Not Started

## Database
ID | Module | Feature | Task | Priority | Dependencies | Assigned To | Status
DB-001 | Authentication Domain | users | Create `users` table migration (columns, PK, FK, timestamps — Document 04) | 🟥 Critical | None |  | 🟦 In Progress
DB-002 | Authentication Domain | roles | Create `roles` table migration (columns, PK, FK, timestamps — Document 04) | 🟧 High | None |  | 🟦 In Progress
DB-003 | Authentication Domain | permissions | Create `permissions` table migration (columns, PK, FK, timestamps — Document 04) | 🟧 High | None |  | 🟦 In Progress
DB-004 | Authentication Domain | role_permissions | Create `role_permissions` table migration (columns, PK, FK, timestamps — Document 04) | 🟧 High | None |  | 🟦 In Progress
DB-005 | Authentication Domain | user_roles | Create `user_roles` table migration (columns, PK, FK, timestamps — Document 04) | 🟧 High | None |  | 🟦 In Progress
DB-006 | Authentication Domain | refresh_tokens | Create `refresh_tokens` table migration (columns, PK, FK, timestamps — Document 04) | 🟧 High | None |  | 🟦 In Progress
DB-007 | Authentication Domain | login_history | Create `login_history` table migration (columns, PK, FK, timestamps — Document 04) | 🟧 High | None |  | 🟦 In Progress
DB-008 | Authentication Domain | password_reset_tokens | Create `password_reset_tokens` table migration (columns, PK, FK, timestamps — Document 04) | 🟧 High | None |  | 🟦 In Progress
DB-009 | Business Domain | businesses | Create `businesses` table migration (columns, PK, FK, timestamps — Document 04) | 🟥 Critical | None |  | ⬜ Not Started
DB-010 | Business Domain | business_profiles | Create `business_profiles` table migration (columns, PK, FK, timestamps — Document 04) | 🟧 High | None |  | ⬜ Not Started
DB-011 | Business Domain | business_addresses | Create `business_addresses` table migration (columns, PK, FK, timestamps — Document 04) | 🟧 High | None |  | ⬜ Not Started
DB-012 | Business Domain | business_categories | Create `business_categories` table migration (columns, PK, FK, timestamps — Document 04) | 🟧 High | None |  | ⬜ Not Started
DB-013 | Business Domain | business_documents | Create `business_documents` table migration (columns, PK, FK, timestamps — Document 04) | 🟧 High | None |  | ⬜ Not Started
DB-014 | Business Domain | business_settings | Create `business_settings` table migration (columns, PK, FK, timestamps — Document 04) | 🟧 High | None |  | ⬜ Not Started
DB-015 | Business Domain | business_bookmarks | Create `business_bookmarks` table migration (columns, PK, FK, timestamps — Document 04) | 🟧 High | None |  | ⬜ Not Started
DB-016 | Supplier Domain | suppliers | Create `suppliers` table migration (columns, PK, FK, timestamps — Document 04) | 🟥 Critical | None |  | ⬜ Not Started
DB-017 | Supplier Domain | supplier_profiles | Create `supplier_profiles` table migration (columns, PK, FK, timestamps — Document 04) | 🟧 High | None |  | ⬜ Not Started
DB-018 | Supplier Domain | supplier_categories | Create `supplier_categories` table migration (columns, PK, FK, timestamps — Document 04) | 🟧 High | None |  | ⬜ Not Started
DB-019 | Supplier Domain | supplier_products | Create `supplier_products` table migration (columns, PK, FK, timestamps — Document 04) | 🟥 Critical | None |  | ⬜ Not Started
DB-020 | Supplier Domain | supplier_product_images | Create `supplier_product_images` table migration (columns, PK, FK, timestamps — Document 04) | 🟧 High | None |  | ⬜ Not Started
DB-021 | Supplier Domain | supplier_delivery_regions | Create `supplier_delivery_regions` table migration (columns, PK, FK, timestamps — Document 04) | 🟧 High | None |  | ⬜ Not Started
DB-022 | Supplier Domain | supplier_business_hours | Create `supplier_business_hours` table migration (columns, PK, FK, timestamps — Document 04) | 🟧 High | None |  | ⬜ Not Started
DB-023 | Supplier Domain | supplier_updates | Create `supplier_updates` table migration (columns, PK, FK, timestamps — Document 04) | 🟧 High | None |  | ⬜ Not Started
DB-024 | Marketplace Domain | orders | Create `orders` table migration (columns, PK, FK, timestamps — Document 04) | 🟥 Critical | None |  | ⬜ Not Started
DB-025 | Marketplace Domain | order_items | Create `order_items` table migration (columns, PK, FK, timestamps — Document 04) | 🟥 Critical | None |  | ⬜ Not Started
DB-026 | Marketplace Domain | business_questions | Create `business_questions` table migration (columns, PK, FK, timestamps — Document 04) | 🟧 High | None |  | ⬜ Not Started
DB-027 | Marketplace Domain | supplier_responses | Create `supplier_responses` table migration (columns, PK, FK, timestamps — Document 04) | 🟧 High | None |  | ⬜ Not Started
DB-028 | Marketplace Domain | product_views | Create `product_views` table migration (columns, PK, FK, timestamps — Document 04) | 🟧 High | None |  | ⬜ Not Started
DB-029 | Marketplace Domain | saved_products | Create `saved_products` table migration (columns, PK, FK, timestamps — Document 04) | 🟧 High | None |  | ⬜ Not Started
DB-030 | Marketplace Domain | saved_suppliers | Create `saved_suppliers` table migration (columns, PK, FK, timestamps — Document 04) | 🟧 High | None |  | ⬜ Not Started
DB-031 | Trust Domain | business_supplier_relationships | Create `business_supplier_relationships` table migration (columns, PK, FK, timestamps — Document 04) | 🟥 Critical | None |  | ⬜ Not Started
DB-032 | Trust Domain | relationship_events | Create `relationship_events` table migration (columns, PK, FK, timestamps — Document 04) | 🟧 High | None |  | ⬜ Not Started
DB-033 | Trust Domain | trust_signals | Create `trust_signals` table migration (columns, PK, FK, timestamps — Document 04) | 🟧 High | None |  | ⬜ Not Started
DB-034 | Trust Domain | business_health_scores | Create `business_health_scores` table migration (columns, PK, FK, timestamps — Document 04) | 🟧 High | None |  | ⬜ Not Started
DB-035 | Trust Domain | supplier_reputation_scores | Create `supplier_reputation_scores` table migration (columns, PK, FK, timestamps — Document 04) | 🟧 High | None |  | ⬜ Not Started
DB-036 | Trust Domain | trust_score_history | Create `trust_score_history` table migration (columns, PK, FK, timestamps — Document 04) | 🟧 High | None |  | ⬜ Not Started
DB-037 | Verification Domain | verification_requests | Create `verification_requests` table migration (columns, PK, FK, timestamps — Document 04) | 🟧 High | None |  | ⬜ Not Started
DB-038 | Verification Domain | verification_documents | Create `verification_documents` table migration (columns, PK, FK, timestamps — Document 04) | 🟧 High | None |  | ⬜ Not Started
DB-039 | Verification Domain | verification_history | Create `verification_history` table migration (columns, PK, FK, timestamps — Document 04) | 🟧 High | None |  | ⬜ Not Started
DB-040 | Platform Domain | notifications | Create `notifications` table migration (columns, PK, FK, timestamps — Document 04) | 🟧 High | None |  | ⬜ Not Started
DB-041 | Platform Domain | notification_preferences | Create `notification_preferences` table migration (columns, PK, FK, timestamps — Document 04) | 🟨 Medium | None |  | ⬜ Not Started
DB-042 | Platform Domain | audit_logs | Create `audit_logs` table migration (columns, PK, FK, timestamps — Document 04) | 🟨 Medium | None |  | ⬜ Not Started
DB-043 | Platform Domain | system_settings | Create `system_settings` table migration (columns, PK, FK, timestamps — Document 04) | 🟨 Medium | None |  | ⬜ Not Started
DB-044 | Platform Domain | lookup_categories | Create `lookup_categories` table migration (columns, PK, FK, timestamps — Document 04) | 🟨 Medium | None |  | ⬜ Not Started
DB-045 | Platform Domain | provinces | Create `provinces` table migration (columns, PK, FK, timestamps — Document 04) | 🟨 Medium | None |  | ⬜ Not Started
DB-046 | Platform Domain | cities | Create `cities` table migration (columns, PK, FK, timestamps — Document 04) | 🟨 Medium | None |  | ⬜ Not Started
DB-047 | Authentication Domain | role_permissions | Add composite primary key (role_id, permission_id) on `role_permissions` | 🟧 High | DB-004 |  | ⬜ Not Started
DB-048 | Authentication Domain | user_roles | Add composite primary key (user_id, role_id) on `user_roles` | 🟧 High | DB-005 |  | ⬜ Not Started
DB-049 | Business Domain | business_bookmarks | Add unique constraint (business_id, supplier_id) on `business_bookmarks` | 🟧 High | DB-015 |  | ⬜ Not Started
DB-050 | Marketplace Domain | saved_products | Add unique constraint (business_id, product_id) on `saved_products` | 🟧 High | DB-029 |  | ⬜ Not Started
DB-051 | Marketplace Domain | saved_suppliers | Add unique constraint (business_id, supplier_id) on `saved_suppliers` | 🟧 High | DB-030 |  | ⬜ Not Started
DB-052 | Trust Domain | business_supplier_relationships | Add unique constraint (business_id, supplier_id) on `business_supplier_relationships` | 🟧 High | DB-031 |  | ⬜ Not Started
DB-053 | Cross-Domain | Soft Delete | Add is_deleted/deleted_at columns to businesses, suppliers, orders, verification_requests (Document 04 §7 note 4) | 🟥 Critical | None |  | ⬜ Not Started
DB-054 | Cross-Domain | Audit Fields | Verify created_at/updated_at defaults are present on every table (Document 04 §1) | 🟨 Medium | None |  | ⬜ Not Started
DB-055 | Platform Domain | Seed Data | Seed `roles` and `permissions` tables (business, supplier, admin, financial_partner — Document 04 §4.1) | 🟥 Critical | DB-002 |  | ⬜ Not Started
DB-056 | Platform Domain | Seed Data | Seed `lookup_categories` reference data (applies_to: business, supplier, product — Document 04 §4.7) | 🟧 High | DB-044 |  | ⬜ Not Started
DB-057 | Platform Domain | Seed Data | Seed `provinces` and `cities` reference data for South Africa (Document 04 §4.7) | 🟧 High | DB-045 |  | ⬜ Not Started
DB-058 | Cross-Domain | Future-Scoped Schema | Reserve Financial Domain placeholder tables (wallets, wallet_transactions, credit_applications) per Document 04 §6 — no implementation in Phase 1 | 🟩 Low | None |  | ⬜ Not Started

## API
ID | Module | Feature | Task | Priority | Dependencies | Assigned To | Status
API-001 | Authentication Domain | auth | POST /auth/register — Create account; role assigned via user_roles at registration | 🟥 Critical | DB-001 |  | 🟦 In Progress
API-002 | Authentication Domain | auth | POST /auth/login — Authenticate with email/password; record login_history; return JWT + refresh token | 🟥 Critical | DB-001 |  | 🟦 In Progress
API-003 | Authentication Domain | auth | POST /auth/google — Authenticate/register via Google OAuth token; return JWT + refresh token | 🟥 Critical | DB-001 |  | 🟦 In Progress
API-004 | Authentication Domain | auth | POST /auth/refresh — Exchange a valid refresh_token for a new JWT | 🟥 Critical | DB-001 |  | 🟦 In Progress
API-005 | Authentication Domain | auth | POST /auth/logout — Revoke the current refresh_token | 🟥 Critical | DB-001 |  | 🟦 In Progress
API-006 | Authentication Domain | auth | POST /auth/forgot-password — Initiate password reset flow; create password_reset_tokens entry | 🟥 Critical | DB-001 |  | 🟦 In Progress
API-007 | Authentication Domain | auth | POST /auth/reset-password — Complete password reset flow using a valid reset token | 🟥 Critical | DB-001 |  | 🟦 In Progress
API-008 | Authentication Domain | auth | GET /auth/me/roles — List roles assigned to the authenticated user | 🟥 Critical | DB-001 |  | 🟦 In Progress
API-009 | Authentication Domain | auth | GET /auth/me/login-history — List recent login_history entries for the authenticated user | 🟥 Critical | DB-001 |  | 🟦 In Progress
API-010 | Business Domain | businesses | GET /businesses/me — Get authenticated business's own profile | 🟧 High | DB-009 |  | ⬜ Not Started
API-011 | Business Domain | businesses | PUT /businesses/me — Update own business profile | 🟧 High | DB-009 |  | ⬜ Not Started
API-012 | Business Domain | businesses | GET /businesses/me/dashboard — Aggregated dashboard payload (today's orders, pending orders, nearby suppliers, recommended products, recent activity) | 🟧 High | DB-009 |  | ⬜ Not Started
API-013 | Business Domain | businesses | GET /businesses/me/profile — Get own Digital Business Profile (read-only, system-generated) | 🟧 High | DB-009 |  | ⬜ Not Started
API-014 | Business Domain | businesses | GET /businesses/{id} — Get public-safe view of a business (supplier-facing, Business Privacy rules) | 🟧 High | DB-009 |  | ⬜ Not Started
API-015 | Business Domain | businesses | GET /businesses/me/addresses — List own business_addresses | 🟧 High | DB-009 |  | ⬜ Not Started
API-016 | Business Domain | businesses | POST /businesses/me/addresses — Add a new business address | 🟧 High | DB-009 |  | ⬜ Not Started
API-017 | Business Domain | businesses | PUT /businesses/me/addresses/{id} — Update a business address | 🟧 High | DB-009 |  | ⬜ Not Started
API-018 | Business Domain | businesses | DELETE /businesses/me/addresses/{id} — Remove a business address | 🟧 High | DB-009 |  | ⬜ Not Started
API-019 | Business Domain | businesses | PUT /businesses/me/addresses/{id}/primary — Set an address as primary/default | 🟧 High | DB-009 |  | ⬜ Not Started
API-020 | Business Domain | businesses | GET /businesses/me/categories — List own business_categories | 🟧 High | DB-009 |  | ⬜ Not Started
API-021 | Business Domain | businesses | PUT /businesses/me/categories — Update own business category assignment(s) | 🟧 High | DB-009 |  | ⬜ Not Started
API-022 | Business Domain | businesses | GET /businesses/me/documents — List own business_documents | 🟧 High | DB-009 |  | ⬜ Not Started
API-023 | Business Domain | businesses | POST /businesses/me/documents — Upload a new business document | 🟧 High | DB-009 |  | ⬜ Not Started
API-024 | Business Domain | businesses | DELETE /businesses/me/documents/{id} — Remove a business document | 🟧 High | DB-009 |  | ⬜ Not Started
API-025 | Business Domain | businesses | GET /businesses/me/settings — Get own business_settings | 🟧 High | DB-009 |  | ⬜ Not Started
API-026 | Business Domain | businesses | PUT /businesses/me/settings — Update own business_settings | 🟧 High | DB-009 |  | ⬜ Not Started
API-027 | Business Domain | businesses | POST /businesses/me/bookmarks — Create a business_bookmarks entry | 🟧 High | DB-009 |  | ⬜ Not Started
API-028 | Business Domain | businesses | DELETE /businesses/me/bookmarks/{id} — Remove a bookmark | 🟧 High | DB-009 |  | ⬜ Not Started
API-029 | Business Domain | businesses | GET /businesses/me/bookmarks — List own bookmarks | 🟧 High | DB-009 |  | ⬜ Not Started
API-030 | Supplier Domain | suppliers | GET /suppliers/me — Get authenticated supplier's own profile | 🟧 High | DB-016 |  | ⬜ Not Started
API-031 | Supplier Domain | suppliers | PUT /suppliers/me — Update own supplier profile | 🟧 High | DB-016 |  | ⬜ Not Started
API-032 | Supplier Domain | suppliers | GET /suppliers/me/dashboard — Aggregated dashboard payload (orders, enquiries, top products, performance) | 🟧 High | DB-016 |  | ⬜ Not Started
API-033 | Supplier Domain | suppliers | GET /suppliers/me/performance — Get own supplier_profiles performance statistics | 🟧 High | DB-016 |  | ⬜ Not Started
API-034 | Supplier Domain | suppliers | GET /suppliers — List/search suppliers (business-facing discovery); filters: category, province, city, verified_only, keyword | 🟧 High | DB-016 |  | ⬜ Not Started
API-035 | Supplier Domain | suppliers | GET /suppliers/{id} — Get public supplier profile (business-facing view) | 🟧 High | DB-016 |  | ⬜ Not Started
API-036 | Supplier Domain | suppliers | GET /suppliers/featured — Featured suppliers list | 🟧 High | DB-016 |  | ⬜ Not Started
API-037 | Supplier Domain | suppliers | GET /suppliers/nearby — Nearby suppliers based on business location | 🟧 High | DB-016 |  | ⬜ Not Started
API-038 | Supplier Domain | suppliers | GET /suppliers/me/categories — List own supplier_categories | 🟧 High | DB-016 |  | ⬜ Not Started
API-039 | Supplier Domain | suppliers | PUT /suppliers/me/categories — Update own supplier category assignment(s) | 🟧 High | DB-016 |  | ⬜ Not Started
API-040 | Supplier Domain | suppliers | GET /suppliers/me/delivery-regions — List own supplier_delivery_regions | 🟧 High | DB-016 |  | ⬜ Not Started
API-041 | Supplier Domain | suppliers | POST /suppliers/me/delivery-regions — Add a delivery region | 🟧 High | DB-016 |  | ⬜ Not Started
API-042 | Supplier Domain | suppliers | DELETE /suppliers/me/delivery-regions/{id} — Remove a delivery region | 🟧 High | DB-016 |  | ⬜ Not Started
API-043 | Supplier Domain | suppliers | GET /suppliers/me/business-hours — List own supplier_business_hours | 🟧 High | DB-016 |  | ⬜ Not Started
API-044 | Supplier Domain | suppliers | PUT /suppliers/me/business-hours — Update business hours (full week payload) | 🟧 High | DB-016 |  | ⬜ Not Started
API-045 | Supplier Domain | products | GET /products — Search/list supplier_products; filters: category, supplier_id, keyword, price range | 🟧 High | DB-016 |  | ⬜ Not Started
API-046 | Supplier Domain | products | GET /products/popular — Popular products listing | 🟧 High | DB-016 |  | ⬜ Not Started
API-047 | Supplier Domain | products | GET /products/recommended — Recommended products for the authenticated business | 🟧 High | DB-016 |  | ⬜ Not Started
API-048 | Supplier Domain | products | GET /products/{id} — Get product detail, including business_questions thread and images | 🟧 High | DB-016 |  | ⬜ Not Started
API-049 | Supplier Domain | products | POST /products — Create a supplier_products entry (supplier only) | 🟧 High | DB-016 |  | ⬜ Not Started
API-050 | Supplier Domain | products | PUT /products/{id} — Update a product (supplier only, own product) | 🟧 High | DB-016 |  | ⬜ Not Started
API-051 | Supplier Domain | products | DELETE /products/{id} — Soft-delete/unpublish a product (supplier only, own product) | 🟧 High | DB-016 |  | ⬜ Not Started
API-052 | Supplier Domain | products | PUT /products/{id}/availability — Toggle stock_status (supplier only) | 🟧 High | DB-016 |  | ⬜ Not Started
API-053 | Supplier Domain | products | POST /products/{id}/images — Add a supplier_product_images entry | 🟧 High | DB-016 |  | ⬜ Not Started
API-054 | Supplier Domain | products | DELETE /products/{id}/images/{image_id} — Remove a product image | 🟧 High | DB-016 |  | ⬜ Not Started
API-055 | Supplier Domain | supplier-updates | POST /supplier-updates — Publish a new supplier_updates entry (supplier only) | 🟧 High | DB-016 |  | ⬜ Not Started
API-056 | Supplier Domain | supplier-updates | GET /supplier-updates/mine — List own published updates (supplier only) | 🟧 High | DB-016 |  | ⬜ Not Started
API-057 | Supplier Domain | suppliers | GET /suppliers/{id}/updates — List a supplier's published updates (business-facing, public) | 🟧 High | DB-016 |  | ⬜ Not Started
API-058 | Marketplace Domain | orders | POST /orders — Place a new order (business only) | 🟥 Critical | DB-024 |  | ⬜ Not Started
API-059 | Marketplace Domain | orders | GET /orders — List orders for the authenticated user, filterable by status | 🟥 Critical | DB-024 |  | ⬜ Not Started
API-060 | Marketplace Domain | orders | GET /orders/{id} — Get order detail, including order_items and delivery tracking status | 🟥 Critical | DB-024 |  | ⬜ Not Started
API-061 | Marketplace Domain | orders | PUT /orders/{id}/accept — Accept an order (supplier only) | 🟥 Critical | DB-024 |  | ⬜ Not Started
API-062 | Marketplace Domain | orders | PUT /orders/{id}/reject — Reject an order (supplier only, requires reason) | 🟥 Critical | DB-024 |  | ⬜ Not Started
API-063 | Marketplace Domain | orders | PUT /orders/{id}/cancel — Cancel an order (business only, subject to workflow rules) | 🟥 Critical | DB-024 |  | ⬜ Not Started
API-064 | Marketplace Domain | orders | PUT /orders/{id}/complete — Mark an order as completed | 🟥 Critical | DB-024 |  | ⬜ Not Started
API-065 | Marketplace Domain | orders | GET /orders/{id}/invoice — Retrieve invoice for a completed order | 🟥 Critical | DB-024 |  | ⬜ Not Started
API-066 | Marketplace Domain | orders | GET /orders/{id}/tracking — Retrieve delivery tracking status | 🟥 Critical | DB-024 |  | ⬜ Not Started
API-067 | Marketplace Domain | products | POST /products/{id}/questions — Submit a business_questions entry on a product (business only) | 🟥 Critical | DB-024 |  | ⬜ Not Started
API-068 | Marketplace Domain | products | GET /products/{id}/questions — List business_questions and their supplier_responses for a product (public) | 🟥 Critical | DB-024 |  | ⬜ Not Started
API-069 | Marketplace Domain | questions | POST /questions/{id}/responses — Submit a supplier_responses entry (supplier only, must own product) | 🟥 Critical | DB-024 |  | ⬜ Not Started
API-070 | Marketplace Domain | businesses | GET /businesses/me/questions — List questions asked by the authenticated business | 🟥 Critical | DB-024 |  | ⬜ Not Started
API-071 | Marketplace Domain | suppliers | GET /suppliers/me/questions — List unanswered/answered questions across the supplier's products | 🟥 Critical | DB-024 |  | ⬜ Not Started
API-072 | Marketplace Domain | products | POST /products/{id}/views — Record a product_views event (business only) | 🟥 Critical | DB-024 |  | ⬜ Not Started
API-073 | Marketplace Domain | businesses | GET /businesses/me/recently-viewed — List recently viewed products | 🟥 Critical | DB-024 |  | ⬜ Not Started
API-074 | Marketplace Domain | saved-products | POST /saved-products — Save a product (business only) | 🟥 Critical | DB-024 |  | ⬜ Not Started
API-075 | Marketplace Domain | saved-products | DELETE /saved-products/{product_id} — Remove a saved product | 🟥 Critical | DB-024 |  | ⬜ Not Started
API-076 | Marketplace Domain | saved-products | GET /saved-products — List the authenticated business's saved products | 🟥 Critical | DB-024 |  | ⬜ Not Started
API-077 | Marketplace Domain | saved-suppliers | POST /saved-suppliers — Follow/save a supplier (business only) | 🟥 Critical | DB-024 |  | ⬜ Not Started
API-078 | Marketplace Domain | saved-suppliers | DELETE /saved-suppliers/{supplier_id} — Unfollow/remove a saved supplier | 🟥 Critical | DB-024 |  | ⬜ Not Started
API-079 | Marketplace Domain | saved-suppliers | GET /saved-suppliers — List the authenticated business's saved/followed suppliers | 🟥 Critical | DB-024 |  | ⬜ Not Started
API-080 | Trust Domain | businesses | GET /businesses/me/relationships — List the authenticated business's business_supplier_relationships | 🟨 Medium | DB-031 |  | ⬜ Not Started
API-081 | Trust Domain | businesses | GET /businesses/me/relationships/{supplier_id} — Get relationship detail with a specific supplier | 🟨 Medium | DB-031 |  | ⬜ Not Started
API-082 | Trust Domain | suppliers | GET /suppliers/me/relationships — List the authenticated supplier's relationships with businesses | 🟨 Medium | DB-031 |  | ⬜ Not Started
API-083 | Trust Domain | businesses | GET /businesses/me/health-score — Get current business_health_scores entry | 🟨 Medium | DB-031 |  | ⬜ Not Started
API-084 | Trust Domain | businesses | GET /businesses/me/health-score/history — Get trust_score_history for the authenticated business | 🟨 Medium | DB-031 |  | ⬜ Not Started
API-085 | Trust Domain | suppliers | GET /suppliers/me/reputation-score — Get current supplier_reputation_scores entry | 🟨 Medium | DB-031 |  | ⬜ Not Started
API-086 | Trust Domain | suppliers | GET /suppliers/me/reputation-score/history — Get trust_score_history for the authenticated supplier | 🟨 Medium | DB-031 |  | ⬜ Not Started
API-087 | Verification Domain | verification | POST /verification/requests — Submit a new verification_requests entry with documents | 🟧 High | DB-037 |  | ⬜ Not Started
API-088 | Verification Domain | verification | GET /verification/requests/mine — List the authenticated account's own verification requests | 🟧 High | DB-037 |  | ⬜ Not Started
API-089 | Verification Domain | verification | GET /verification/requests/{id} — Get a specific verification request, including documents and history | 🟧 High | DB-037 |  | ⬜ Not Started
API-090 | Verification Domain | verification | POST /verification/requests/{id}/documents — Add an additional supporting document to an existing request | 🟧 High | DB-037 |  | ⬜ Not Started
API-091 | Platform Domain | notifications | GET /notifications — List notifications for the authenticated user, paginated | 🟨 Medium | DB-040 |  | ⬜ Not Started
API-092 | Platform Domain | notifications | PUT /notifications/{id}/read — Mark a notification as read | 🟨 Medium | DB-040 |  | ⬜ Not Started
API-093 | Platform Domain | notifications | PUT /notifications/read-all — Mark all notifications as read | 🟨 Medium | DB-040 |  | ⬜ Not Started
API-094 | Platform Domain | notifications | GET /notifications/unread-count — Get unread notification count | 🟨 Medium | DB-040 |  | ⬜ Not Started
API-095 | Platform Domain | notification-preferences | GET /notification-preferences — Get the authenticated user's notification_preferences | 🟨 Medium | DB-040 |  | ⬜ Not Started
API-096 | Platform Domain | notification-preferences | PUT /notification-preferences — Update notification preferences (per type/channel) | 🟨 Medium | DB-040 |  | ⬜ Not Started
API-097 | Platform Domain | categories | GET /categories — List lookup_categories, filterable by applies_to | 🟨 Medium | DB-040 |  | ⬜ Not Started
API-098 | Platform Domain | provinces | GET /provinces — List provinces | 🟨 Medium | DB-040 |  | ⬜ Not Started
API-099 | Platform Domain | provinces | GET /provinces/{id}/cities — List cities within a province | 🟨 Medium | DB-040 |  | ⬜ Not Started

## Trust Engine
ID | Module | Feature | Task | Priority | Dependencies | Assigned To | Status
TE-001 | Trust Domain | Digital Business Profile | Calculate orders_count (completed orders only) — Document 07 §2 | 🟧 High | Order/Question/Verification event pipeline |  | ⬜ Not Started
TE-002 | Trust Domain | Digital Business Profile | Calculate suppliers_count (distinct suppliers with ≥1 completed order) — Document 07 §2 | 🟧 High | Order/Question/Verification event pipeline |  | ⬜ Not Started
TE-003 | Trust Domain | Digital Business Profile | Calculate average_order_value — Document 07 §2 | 🟧 High | Order/Question/Verification event pipeline |  | ⬜ Not Started
TE-004 | Trust Domain | Digital Business Profile | Calculate largest_order_value — Document 07 §2 | 🟨 Medium | Order/Question/Verification event pipeline |  | ⬜ Not Started
TE-005 | Trust Domain | Digital Business Profile | Calculate repeat_supplier_rate — Document 07 §2 | 🟧 High | Order/Question/Verification event pipeline |  | ⬜ Not Started
TE-006 | Trust Domain | Digital Business Profile | Calculate average_payment_time_days (Phase 1 proxy: order completion time) — Document 07 §2 | 🟨 Medium | Order/Question/Verification event pipeline |  | ⬜ Not Started
TE-007 | Trust Domain | Digital Business Profile | Calculate business_growth_percentage (rolling period volume/value change) — Document 07 §2 | 🟧 High | Order/Question/Verification event pipeline |  | ⬜ Not Started
TE-008 | Trust Domain | Digital Business Profile | Derive Risk Level (low/medium/high) from Trust + Risk Signals — Document 07 §2, §6 | 🟧 High | Order/Question/Verification event pipeline |  | ⬜ Not Started
TE-009 | Trust Domain | Relationship Health | Signal: order frequency between business-supplier pair — Document 07 §3 | 🟧 High | Order/Question/Verification event pipeline |  | ⬜ Not Started
TE-010 | Trust Domain | Relationship Health | Signal: recency of last interaction — Document 07 §3 | 🟧 High | Order/Question/Verification event pipeline |  | ⬜ Not Started
TE-011 | Trust Domain | Relationship Health | Signal: order completion rate within the pair — Document 07 §3 | 🟧 High | Order/Question/Verification event pipeline |  | ⬜ Not Started
TE-012 | Trust Domain | Relationship Health | Signal: Business Question responsiveness between the pair — Document 07 §3 | 🟨 Medium | Order/Question/Verification event pipeline |  | ⬜ Not Started
TE-013 | Trust Domain | Relationship Health | Composite relationship_health_score calculation — Document 07 §3 | 🟧 High | Order/Question/Verification event pipeline |  | ⬜ Not Started
TE-014 | Trust Domain | Repeat Orders | Weight repeat completed orders more heavily than first-time orders — Document 07 §4 | 🟧 High | Order/Question/Verification event pipeline |  | ⬜ Not Started
TE-015 | Trust Domain | Product Views | Feed "Recently Viewed" personalisation from product_views — Document 07 §5 | 🟨 Medium | Order/Question/Verification event pipeline |  | ⬜ Not Started
TE-016 | Trust Domain | Product Views | Feed product/supplier popularity ranking from product_views — Document 07 §5 | 🟨 Medium | Order/Question/Verification event pipeline |  | ⬜ Not Started
TE-017 | Trust Domain | Product Views | Store product_views as early-stage interest signal for future recommendation training — Document 07 §5 | 🟩 Low | Order/Question/Verification event pipeline |  | ⬜ Not Started
TE-018 | Trust Domain | Business Questions Signals | Calculate average_response_time_minutes — Document 07 §6.2 | 🟧 High | Order/Question/Verification event pipeline |  | ⬜ Not Started
TE-019 | Trust Domain | Business Questions Signals | Calculate response_rate_percentage — Document 07 §6.2 | 🟧 High | Order/Question/Verification event pipeline |  | ⬜ Not Started
TE-020 | Trust Domain | Business Questions Signals | Score engagement signal for asking business — Document 07 §6.1 | 🟩 Low | Order/Question/Verification event pipeline |  | ⬜ Not Started
TE-021 | Trust Domain | Order Behaviour | Track order frequency/volume trend per business — Document 07 §7 | 🟨 Medium | Order/Question/Verification event pipeline |  | ⬜ Not Started
TE-022 | Trust Domain | Order Behaviour | Track sourcing concentration vs. diversification per business — Document 07 §7 | 🟩 Low | Order/Question/Verification event pipeline |  | ⬜ Not Started
TE-023 | Trust Domain | Order Behaviour | Track business-initiated cancellation rate — Document 07 §7 | 🟨 Medium | Order/Question/Verification event pipeline |  | ⬜ Not Started
TE-024 | Trust Domain | Order Behaviour | Track order value consistency (variance over time) — Document 07 §7 | 🟩 Low | Order/Question/Verification event pipeline |  | ⬜ Not Started
TE-025 | Trust Domain | Order Behaviour | Track supplier acceptance rate of incoming orders — Document 07 §7 | 🟨 Medium | Order/Question/Verification event pipeline |  | ⬜ Not Started
TE-026 | Trust Domain | Order Behaviour | Track supplier fulfilment completion rate — Document 07 §7 | 🟨 Medium | Order/Question/Verification event pipeline |  | ⬜ Not Started
TE-027 | Trust Domain | Order Behaviour | Track supplier time from acceptance to completion — Document 07 §7 | 🟨 Medium | Order/Question/Verification event pipeline |  | ⬜ Not Started
TE-028 | Trust Domain | Risk & Trust Signals | Populate `trust_signals` table from Trust Signal calculations — Document 07 §8 | 🟧 High | Order/Question/Verification event pipeline |  | ⬜ Not Started
TE-029 | Trust Domain | Risk & Trust Signals | Populate `trust_signals` table from Risk Signal calculations — Document 07 §8 | 🟧 High | Order/Question/Verification event pipeline |  | ⬜ Not Started
TE-030 | Trust Domain | Business Health Score | Weighted composite Business Health Score calculation (versioned methodology) — Document 07 §10 | 🟧 High | Order/Question/Verification event pipeline |  | ⬜ Not Started
TE-031 | Trust Domain | Business Health Score | Store methodology_version on business_health_scores for explainability — Document 07 §10 | 🟨 Medium | Order/Question/Verification event pipeline |  | ⬜ Not Started
TE-032 | Trust Domain | Supplier Reputation | Weighted composite Supplier Reputation calculation — Document 07 §11 | 🟧 High | Order/Question/Verification event pipeline |  | ⬜ Not Started
TE-033 | Trust Domain | Trend History | Append trust_score_history entry on every recalculation — Document 07 (Document 04 §4.5) | 🟨 Medium | Order/Question/Verification event pipeline |  | ⬜ Not Started
TE-034 | Trust Domain | Credit Readiness | Define configurable Credit Readiness threshold parameters (Phase 3 prep, no UI in Phase 1) — Document 07 §13 | 🟩 Low | Order/Question/Verification event pipeline |  | ⬜ Not Started

## Testing
ID | Module | Feature | Task | Priority | Dependencies | Assigned To | Status
QA-001 | Authentication Domain | Unit Tests | Auth unit & integration tests — register, login, refresh, logout | 🟥 Critical | Corresponding implementation task complete |  | 🟨 Testing
QA-002 | Authentication Domain | Security Tests | JWT validation & role-based access control tests | 🟥 Critical | Corresponding implementation task complete |  | 🟨 Testing
QA-003 | Business Domain | Unit Tests | Business Service unit tests (profile CRUD, addresses, documents) | 🟧 High | Corresponding implementation task complete |  | ⬜ Not Started
QA-004 | Business Domain | Repository Tests | Business Repository tests against seeded database | 🟨 Medium | Corresponding implementation task complete |  | ⬜ Not Started
QA-005 | Supplier Domain | Unit Tests | Product Service unit tests (create/update/publish/soft-delete) | 🟧 High | Corresponding implementation task complete |  | ⬜ Not Started
QA-006 | Supplier Domain | Repository Tests | Supplier Repository tests against seeded database | 🟨 Medium | Corresponding implementation task complete |  | ⬜ Not Started
QA-007 | Marketplace Domain | Integration Tests | Order lifecycle integration test (place → accept → complete) | 🟥 Critical | Corresponding implementation task complete |  | ⬜ Not Started
QA-008 | Marketplace Domain | Integration Tests | Order rejection workflow integration test | 🟧 High | Corresponding implementation task complete |  | ⬜ Not Started
QA-009 | Marketplace Domain | Integration Tests | Business Question + Supplier Response workflow test | 🟧 High | Corresponding implementation task complete |  | ⬜ Not Started
QA-010 | Marketplace Domain | Business Rule Tests | Enforce single-supplier-cart rule test (Document 06 §10) | 🟧 High | Corresponding implementation task complete |  | ⬜ Not Started
QA-011 | Marketplace Domain | Business Rule Tests | Enforce minimum order quantity validation test (Document 06 §10) | 🟧 High | Corresponding implementation task complete |  | ⬜ Not Started
QA-012 | Trust Domain | Unit Tests | Business Health Score calculation unit tests | 🟧 High | Corresponding implementation task complete |  | ⬜ Not Started
QA-013 | Trust Domain | Unit Tests | Relationship Health Score calculation unit tests | 🟧 High | Corresponding implementation task complete |  | ⬜ Not Started
QA-014 | Trust Domain | Unit Tests | Supplier Reputation calculation unit tests | 🟨 Medium | Corresponding implementation task complete |  | ⬜ Not Started
QA-015 | Verification Domain | Business Rule Tests | Verification approve/reject workflow test (Document 06 §3) | 🟧 High | Corresponding implementation task complete |  | ⬜ Not Started
QA-016 | Platform Domain | Integration Tests | Notification delivery rules test (Document 06 §18) | 🟨 Medium | Corresponding implementation task complete |  | ⬜ Not Started
QA-017 | API | API Tests | Contract tests for all Authentication Domain endpoints | 🟥 Critical | Corresponding implementation task complete |  | ⬜ Not Started
QA-018 | API | API Tests | Contract tests for all Business Domain endpoints | 🟧 High | Corresponding implementation task complete |  | ⬜ Not Started
QA-019 | API | API Tests | Contract tests for all Supplier Domain endpoints | 🟧 High | Corresponding implementation task complete |  | ⬜ Not Started
QA-020 | API | API Tests | Contract tests for all Marketplace Domain endpoints | 🟥 Critical | Corresponding implementation task complete |  | ⬜ Not Started
QA-021 | API | API Tests | Contract tests for all Trust Domain endpoints | 🟨 Medium | Corresponding implementation task complete |  | ⬜ Not Started
QA-022 | API | API Tests | Contract tests for all Verification Domain endpoints | 🟧 High | Corresponding implementation task complete |  | ⬜ Not Started
QA-023 | API | API Tests | Contract tests for all Platform Domain endpoints | 🟨 Medium | Corresponding implementation task complete |  | ⬜ Not Started
QA-024 | API | Validation Tests | Pagination + list envelope tests across every list endpoint (Document 05 §1) | 🟨 Medium | Corresponding implementation task complete |  | ⬜ Not Started
QA-025 | Frontend | UI Tests | Business registration + login flow UI test | 🟧 High | Corresponding implementation task complete |  | ⬜ Not Started
QA-026 | Frontend | UI Tests | Supplier product create/edit flow UI test | 🟧 High | Corresponding implementation task complete |  | ⬜ Not Started
QA-027 | Frontend | UI Tests | Place order end-to-end UI test | 🟥 Critical | Corresponding implementation task complete |  | ⬜ Not Started
QA-028 | Frontend | UI Tests | Business Question ask/respond UI test | 🟨 Medium | Corresponding implementation task complete |  | ⬜ Not Started
QA-029 | Frontend | UI Tests | Offline/loading/empty state rendering test across list screens (Document 02 §2.3) | 🟨 Medium | Corresponding implementation task complete |  | ⬜ Not Started
QA-030 | Database | Data Integrity Tests | Soft-delete integrity test (order history preserved after product delete) | 🟧 High | Corresponding implementation task complete |  | ⬜ Not Started
QA-031 | Database | Data Integrity Tests | Unique constraint tests (saved_suppliers, saved_products, business_bookmarks) | 🟨 Medium | Corresponding implementation task complete |  | ⬜ Not Started
QA-032 | Performance | Load Tests | Load test on supplier discovery search under concurrent business traffic | 🟨 Medium | Corresponding implementation task complete |  | ⬜ Not Started
QA-033 | Performance | Load Tests | Load test on async Trust recalculation job queue | 🟨 Medium | Corresponding implementation task complete |  | ⬜ Not Started
QA-034 | Security | Security Tests | SQL injection & input sanitisation sweep across all write endpoints | 🟧 High | Corresponding implementation task complete |  | ⬜ Not Started
QA-035 | Security | Security Tests | Resource-ownership authorization test (supplier cannot edit another supplier's product) | 🟥 Critical | Corresponding implementation task complete |  | ⬜ Not Started

## DevOps
ID | Module | Feature | Task | Priority | Dependencies | Assigned To | Status
OPS-001 | Platform Infrastructure | Environment | Define environment variable schema (.env.example) for backend and mobile | 🟥 Critical | None |  | ⬜ Not Started
OPS-002 | Platform Infrastructure | Environment | Separate development / staging / production configuration profiles | 🟧 High | None |  | ⬜ Not Started
OPS-003 | Platform Infrastructure | Containerization | Dockerize Flask backend service | 🟧 High | None |  | ⬜ Not Started
OPS-004 | Platform Infrastructure | Containerization | Dockerize PostgreSQL with persistent volume | 🟧 High | None |  | ⬜ Not Started
OPS-005 | Platform Infrastructure | CI/CD | CI pipeline — lint + unit test on every pull request | 🟥 Critical | None |  | ⬜ Not Started
OPS-006 | Platform Infrastructure | CI/CD | CI pipeline — build backend Docker image on merge to main | 🟧 High | None |  | ⬜ Not Started
OPS-007 | Platform Infrastructure | CI/CD | CD pipeline — deploy backend to staging environment | 🟧 High | None |  | ⬜ Not Started
OPS-008 | Platform Infrastructure | CI/CD | CD pipeline — deploy backend to production with manual approval gate | 🟧 High | None |  | ⬜ Not Started
OPS-009 | Platform Infrastructure | Database Ops | Automated database migration pipeline (apply on deploy) | 🟥 Critical | None |  | ⬜ Not Started
OPS-010 | Platform Infrastructure | Database Ops | Automated nightly database backups with retention policy | 🟧 High | None |  | ⬜ Not Started
OPS-011 | Platform Infrastructure | Observability | Structured logging pipeline (aggregation + retention) | 🟨 Medium | None |  | ⬜ Not Started
OPS-012 | Platform Infrastructure | Observability | Application monitoring & alerting (error rate, latency) | 🟨 Medium | None |  | ⬜ Not Started
OPS-013 | Platform Infrastructure | Observability | Health check endpoint for backend service | 🟧 High | None |  | ⬜ Not Started
OPS-014 | Platform Infrastructure | Security | Secrets management (API keys, JWT signing keys, DB credentials) | 🟥 Critical | None |  | ⬜ Not Started
OPS-015 | Platform Infrastructure | API Governance | Document /api/v1 versioning strategy for additive, non-breaking expansion (Document 05 §1) | 🟨 Medium | None |  | ⬜ Not Started

## Future Phases
ID | Module | Feature | Task | Priority | Dependencies | Assigned To | Status
FUT-001 | Deferred Phase 1 Endpoints | Authentication | Implement POST /auth/phone/request-otp (Document 05 §5.1, future) | 🟩 Low | Phase 1 completion |  | ⬜ Not Started
FUT-002 | Deferred Phase 1 Endpoints | Authentication | Implement POST /auth/phone/verify-otp (Document 05 §5.1, future) | 🟩 Low | Phase 1 completion |  | ⬜ Not Started
FUT-003 | Deferred Phase 1 Endpoints | Authentication | Implement biometric registration/verification endpoints (Document 05 §5.1, future) | 🟩 Low | Phase 1 completion |  | ⬜ Not Started
FUT-004 | Deferred Phase 1 Endpoints | Authentication | Implement passkey registration endpoints (Document 05 §5.1, future) | 🟩 Low | Phase 1 completion |  | ⬜ Not Started
FUT-005 | Deferred Phase 1 Endpoints | Admin (Platform Administrator role) | Implement GET/PUT /admin/roles, /admin/users/{id}/roles (Document 05 §5.1, Document 01 §9.3) | 🟩 Low | Phase 1 completion |  | ⬜ Not Started
FUT-006 | Deferred Phase 1 Endpoints | Admin (Platform Administrator role) | Implement PUT/GET /admin/verification/requests (Document 05 §5.6, Document 01 §9.3) | 🟩 Low | Phase 1 completion |  | ⬜ Not Started
FUT-007 | Deferred Phase 1 Endpoints | Admin (Platform Administrator role) | Implement GET /admin/audit-logs, /admin/system-settings (Document 05 §5.7, Document 01 §9.3) | 🟩 Low | Phase 1 completion |  | ⬜ Not Started
FUT-008 | Deferred Phase 1 Endpoints | Financial Partner role | Design read-only Financial Partner access model (Document 01 §9.3, Phase 4) | 🟩 Low | Phase 1 completion |  | ⬜ Not Started
FUT-009 | Phase 2 — Payments, Wallet, Insights | Payments | Design and implement in-app payment processing for orders (Document 08) | 🟨 Medium | Phase 1 completion |  | ⬜ Not Started
FUT-010 | Phase 2 — Payments, Wallet, Insights | Wallet | Design Wallet data model in a new Financial Domain (Document 04 §6, Document 08) | 🟨 Medium | Phase 1 completion |  | ⬜ Not Started
FUT-011 | Phase 2 — Payments, Wallet, Insights | Wallet | Implement wallet_transactions ledger (Document 04 §6) | 🟨 Medium | Phase 1 completion |  | ⬜ Not Started
FUT-012 | Phase 2 — Payments, Wallet, Insights | Business Insights | Build Business Insights analytics module on top of Digital Business Profile (Document 08) | 🟨 Medium | Phase 1 completion |  | ⬜ Not Started
FUT-013 | Phase 2 — Payments, Wallet, Insights | Supplier Analytics | Build Supplier Analytics module (demand trends, retention, response-time benchmarking) (Document 08) | 🟨 Medium | Phase 1 completion |  | ⬜ Not Started
FUT-014 | Phase 2 — Payments, Wallet, Insights | Trust Engine Refinement | Replace Average Payment Time proxy with real payment timestamps once Wallet ships (Document 07 §2, Document 08) | 🟨 Medium | Phase 1 completion |  | ⬜ Not Started
FUT-015 | Phase 3 — Credit & Trade Finance | Credit | Design short-term stock financing credit facility (Document 08) | 🟩 Low | Phase 1 completion |  | ⬜ Not Started
FUT-016 | Phase 3 — Credit & Trade Finance | Trade Finance | Design trade finance instruments for recurring supplier transactions (Document 08) | 🟩 Low | Phase 1 completion |  | ⬜ Not Started
FUT-017 | Phase 3 — Credit & Trade Finance | Working Capital | Design supplier working capital facility based on Supplier Reputation (Document 08) | 🟩 Low | Phase 1 completion |  | ⬜ Not Started
FUT-018 | Phase 3 — Credit & Trade Finance | Underwriting | Design underwriting/risk model consuming Trust Signals + Risk Signals (Document 07 §13, Document 08) | 🟩 Low | Phase 1 completion |  | ⬜ Not Started
FUT-019 | Phase 3 — Credit & Trade Finance | Underwriting | Enforce Credit Readiness thresholds as eligibility gate (Document 07 §13) | 🟩 Low | Phase 1 completion |  | ⬜ Not Started
FUT-020 | Phase 3 — Credit & Trade Finance | Compliance | Regulatory and compliance readiness review for credit products (Document 08) | 🟩 Low | Phase 1 completion |  | ⬜ Not Started
FUT-021 | Phase 4 — Partner APIs & Open Platform | Partner APIs | Design permissioned Partner API surface for external data access (Document 08, Document 09 §5) | 🟩 Low | Phase 1 completion |  | ⬜ Not Started
FUT-022 | Phase 4 — Partner APIs & Open Platform | Financial Institutions | Build financial institution integration layer for credit/insurance/savings origination (Document 08) | 🟩 Low | Phase 1 completion |  | ⬜ Not Started
FUT-023 | Phase 4 — Partner APIs & Open Platform | Data Governance | Build data governance, consent, and privacy infrastructure for external sharing (Document 08) | 🟩 Low | Phase 1 completion |  | ⬜ Not Started
FUT-024 | Phase 4 — Partner APIs & Open Platform | Open Platform Expansion | Evaluate adjacent ecosystem services (logistics, insurance) on shared trust infrastructure (Document 08) | 🟩 Low | Phase 1 completion |  | ⬜ Not Started

## Notes & Assumptions
TRU CONNECT: ENGINEERING ROADMAP: NOTES & ASSUMPTIONS
SOURCE OF TRUTH
Every task in this workbook is derived directly from Documents 00–09 (Project Vision, Product Specification, System UI/UX Specification, Frontend Component Specification, Database Design, Backend API Specification, Business Rules & Workflows, Data and Trust Engine, Product Roadmap, Ecosystem Strategy).
DELIBERATE SCOPE EXCLUSIONS
The roadmap-generator prompt template requested sheets/tasks for OCR, Receipt Upload, Invoice Parsing, a Credit Scoring/ML Engine, Fraud Detection, and a general-purpose Analytics Engine. None of these appear anywhere in Documents 00–09: Document 07 (Data and Trust Engine) explicitly states Phase 1 uses transparent, rule-based calculations, not ML models (§9), and Document 08 (Product Roadmap) does not mention receipts, OCR, or invoice parsing at any phase. Per the explicit instruction "Never invent features," this workbook does not include tasks for functionality that has no basis in the documentation. If TRU Connect intends to build these, they need their own source-of-truth documentation first — at that point this workbook can be extended with matching sheets.
GROUNDED PROGRESS
A handful of tasks are pre-marked "In Progress" or "Complete" rather than "Not Started", based on the current repository tree (structure.txt) supplied in this conversation: the Authentication Domain already has scaffolded backend files (user.py, user_repository.py, auth_service.py, auth_routes.py, auth_schemas.py, test_auth.py), backend core infrastructure files exist (config.py, extensions.py, base_model.py, decorators.py, exceptions.py, responses.py, logger.py, security.py), and the Supplier Product Catalogue frontend feature (screens, components, hooks, services, api) has been fully generated. Everything else defaults to Not Started — recalibrate freely as work actually progresses.
ID SCHEME
DB-xxx Database · BE-xxx Backend · API-xxx API · FE-xxx Frontend · TE-xxx Trust Engine · QA-xxx Testing · OPS-xxx DevOps · FUT-xxx Future Phases (2–4).
DEPENDENCIES COLUMN
Dependencies point to the most relevant upstream task or artifact (e.g. a Database migration ID a Backend model depends on). They are indicative of build order, not an exhaustive dependency graph — recalibrate during sprint planning.
HOW TO USE THIS WORKBOOK
1. Update the Status cell on each task as work progresses, use the dropdown (data validation) rather than typing free text, so the Dashboard formulas keep working.
2. The Dashboard sheet recalculates automatically from every other sheet's Status column, no manual totals to maintain.
3. Fill in "Assigned To" as the team takes ownership of tasks; it is intentionally left blank in this initial extraction.
4. Filter any sheet by Module, Priority, or Status using Excel's AutoFilter (enable via Data > Filter) to scope a sprint.